Energy Grid Infrastructure

Log Monitoring & ServiceNow Integration

Project Plan & Requirements

Version 1.0  |  June 2026

# 1. Executive Summary

This document defines the project plan and requirements for building a centralized log monitoring system for energy grid infrastructure equipment. The system will provide both real-time visibility and historical log analysis, triggered and contextualized by ServiceNow maintenance tickets.

Starting from no centralized log system, this project will cover discovery, architecture, deployment, integration, and compliance alignment across OT and IT network boundaries typical of energy grid environments.

# 2. Project Objectives

- Provide real-time log streaming for equipment under active maintenance tickets

- Build a historical log repository queryable by asset, time window, and ticket ID

- Integrate log context into ServiceNow ITSM (work notes, CI enrichment)

- Respect OT/IT security boundaries (air gaps, DMZ, security zones)

- Establish a compliance-ready logging baseline (NERC CIP / IEC 62351 compatible)

- Lay the foundation for alarm correlation and predictive maintenance use cases

# 3. Scope

## 3.1 In Scope

- Substations, RTUs, IEDs, protection relays (IEC 61850, DNP3, Modbus)

- SCADA/EMS/DMS event and alarm logs

- Network equipment within substations (switches, routers, firewalls)

- Historian data correlation (OSIsoft PI / Aveva or equivalent)

- ServiceNow integration via REST API

- Log collection, normalization, storage, and visualization layer

## 3.2 Out of Scope

- Generation asset telemetry (separate SCADA domain)

- Customer-facing systems (AMI, billing)

- Full SIEM deployment (may follow as Phase 2)

- Replacing or modifying existing SCADA/EMS platforms

# 4. Stakeholders

- OT Operations Team — primary users during maintenance windows

- Real-time log consumers, define alerting thresholds

- IT/Network Team — owns IT-side infrastructure and ServiceNow

- Integration owners, syslog server, DMZ architecture

- SCADA Engineering — gatekeepers for OT system access

- Approve protocol access, IED connectivity, historian queries

- Cybersecurity / Compliance — validate architecture against regulatory requirements

- NERC CIP, IEC 62351, internal security policies

- Project Sponsor — budget authority and executive escalation path

# 5. Requirements

## 5.1 Functional Requirements

| ID | Requirement | Acceptance Criteria |
| --- | --- | --- |
| FR-01 | The system shall collect logs from substations and field equipment via standard protocols (syslog, IEC 61850 MMS, SNMP traps, DNP3 events) | Logs received from ≥3 protocol types in a lab environment |
| FR-02 | The system shall provide real-time log streaming filtered by the asset (CI) associated with an active ServiceNow ticket | Logs appear in dashboard within 10 seconds of generation during a test maintenance window |
| FR-03 | The system shall store logs for a configurable retention period (minimum 12 months) | Query successfully retrieves logs 12 months old in test environment |
| FR-04 | The system shall allow log queries by: asset ID, CI name, time range, ticket number, and log severity | All 5 filter dimensions return correct results in acceptance testing |
| FR-05 | The system shall append log summary and key events to the corresponding ServiceNow ticket as work notes via REST API | Work notes updated automatically within 5 minutes of ticket state change to ‘In Maintenance’ |
| FR-06 | The system shall support SOE (Sequence of Events) reconstruction for protection relay events | SOE report generated correctly for a simulated fault event |
| FR-07 | The system shall normalize logs from heterogeneous sources into a common schema | Common fields (timestamp, asset ID, severity, message) present in ≥ 95% of ingested logs |

## 5.2 Non-Functional Requirements

| ID | Requirement | Acceptance Criteria |
| --- | --- | --- |
| NFR-01 | Log ingestion pipeline must operate within the OT security zone without direct internet access | All data flows validated in network diagram; no direct internet egress from OT collectors |
| NFR-02 | The system shall not introduce latency or risk to operational SCADA processes | Log collection uses read-only, passive methods; zero SCADA process disruptions in UAT |
| NFR-03 | Real-time dashboard must support ≥10 concurrent users | Load test passes with 10 simultaneous users, <3s page load |
| NFR-04 | Log storage must be encrypted at rest and in transit | Encryption validated via security review; TLS 1.2+ for all data in transit |
| NFR-05 | System must achieve ≥99.5% uptime during business hours | Uptime monitored and reported monthly; meets SLA in first 3 months post-launch |
| NFR-06 | Architecture must be documented and auditable for compliance reviews | Architecture diagram and data-flow document approved by cybersecurity team |

## 5.3 Integration Requirements

| ID | Requirement | Acceptance Criteria |
| --- | --- | --- |
| IR-01 | ServiceNow REST API integration to read CI data and write work notes | Bidirectional API tested with sandbox ServiceNow instance |
| IR-02 | CMDB sync: asset hostnames/IPs in ServiceNow must map to log sources | Mapping table validated with ≥90% of in-scope assets |
| IR-03 | Historian integration for time-series data correlation (read-only) | Historian tags queryable alongside event logs for same time window |
| IR-04 | IEC 61850 MMS client for IED buffered report blocks (BRCBs) | BRCB subscription tested against a real or simulated IED |

# 6. Architecture Overview

The architecture follows a zone-separated model aligned with IEC 62351 and NERC CIP principles:

OT Zone (Substation / Field)

- Log collectors deployed as read-only agents or passive listeners per substation

- Protocols: syslog UDP/TCP, IEC 61850 MMS, SNMP traps, DNP3 event buffers

- No inbound connections from IT zone to OT zone

DMZ / Data Diode Layer

- One-way data transfer from OT to IT using a data diode or secure jump host

- Log forwarding only; no control-plane traffic allowed

IT Zone (Central Platform)

- Log aggregation platform (e.g., Elastic/OpenSearch, Grafana Loki, or Splunk)

- Normalization pipeline (Logstash, Fluent Bit, or equivalent)

- ServiceNow integration middleware (REST API calls)

- Web-based dashboard for operations and maintenance teams

Technology Candidates

- Log aggregation: Elastic Stack (ELK), Grafana Loki, or Splunk (to be selected in Phase 1)

- Normalization: Logstash / Fluent Bit

- IEC 61850 collector: libIEC61850-based agent or commercial equivalent

- ServiceNow integration: MID Server or direct REST from IT zone

# 7. Phased Project Plan

| Phase | Name | Duration | Key Deliverable |
| --- | --- | --- | --- |
| Phase 0 | Discovery & Assessment | 4–6 weeks | Asset inventory, compliance gap analysis, architecture decision |
| Phase 1 | Architecture & PoC | 6–8 weeks | Approved architecture, working PoC on 1 substation |
| Phase 2 | Core Platform Build | 8–12 weeks | Log pipeline, storage, normalization operational |
| Phase 3 | ServiceNow Integration | 4–6 weeks | Ticket-triggered log views and automated work notes |
| Phase 4 | Rollout & Hardening | 6–8 weeks | Full asset coverage, security review, documentation |
| Phase 5 | Steady State & Compliance | Ongoing | SLA monitoring, retention management, audit support |

## Phase 0 — Discovery & Assessment (Weeks 1–6)

- Inventory all in-scope equipment: substations, IEDs, RTUs, network devices

- Map log sources, protocols, and current data paths

- Identify OT/IT security zones and existing DMZ or data diode infrastructure

- Assess compliance obligations (NERC CIP applicability, internal policies)

- Review ServiceNow CMDB completeness for in-scope CIs

- Select log aggregation platform and confirm tooling budget

## Phase 1 — Architecture & Proof of Concept (Weeks 7–14)

- Finalize architecture with cybersecurity and SCADA engineering sign-off

- Deploy PoC collector at one pilot substation

- Validate IEC 61850, syslog, and SNMP collection in lab or live environment

- Test one-way data transfer through DMZ layer

- Demonstrate basic log dashboard with asset filtering

## Phase 2 — Core Platform Build (Weeks 15–26)

- Deploy and harden central log aggregation platform in IT zone

- Build normalization pipeline for all target protocols

- Implement log retention policy (12 months minimum)

- Configure encryption at rest and in transit

- Deploy collectors across all in-scope substations

## Phase 3 — ServiceNow Integration (Weeks 27–32)

- Map CMDB CIs to log source identifiers

- Build trigger: on ticket state change to ‘In Maintenance’, open scoped log view

- Implement work notes automation via ServiceNow REST API

- Test end-to-end: ticket created → logs scoped → summary posted to ticket

- Build SOE report generation for protection relay events

## Phase 4 — Rollout & Hardening (Weeks 33–40)

- Complete rollout to all substations and field equipment

- Conduct security review and penetration test of log pipeline

- User acceptance testing with operations and maintenance teams

- Finalize documentation: architecture, runbooks, data flow diagrams

- Train OT operations team on dashboard and ticket log views

# 8. Risks & Mitigations

| Risk | Likelihood | Impact | Mitigation |
| --- | --- | --- | --- |
| OT access restrictions delay collector deployment | High | High | Engage SCADA engineering early in Phase 0; use passive read-only collection methods |
| Compliance obligations (NERC CIP) unknown or more stringent than expected | Medium | High | Bring in compliance advisor in Phase 0; design architecture to be CIP-ready from the start |
| CMDB data quality is poor; CIs don’t map to real assets | Medium | Medium | Dedicate time in Phase 0 to CMDB audit; build manual mapping fallback |
| IED log protocols vary by vendor (SEL, ABB, GE, Siemens) | High | Medium | Prototype against 2–3 vendor IEDs in Phase 1 PoC; allocate buffer for protocol edge cases |
| ServiceNow sandbox unavailable for integration testing | Low | Medium | Request dedicated dev/test instance early; use mock API if needed |
| Data volume from substations exceeds platform sizing estimates | Medium | Medium | Size platform with 3x headroom; implement log sampling for high-volume low-priority sources |

# 9. Compliance Considerations

While specific regulatory obligations are still to be confirmed during Phase 0, the following frameworks are likely applicable and should guide architecture decisions from the outset:

- NERC CIP (North America) — if assets are classified as BES Cyber Systems, CIP-007 (system security management) and CIP-010 (configuration management) impose logging and monitoring requirements

- IEC 62351 — defines security for power system communications; relevant for securing IEC 61850 and DNP3 data flows

- ISO 27001 — general information security management; may apply to IT-zone components

- Internal OT Security Policy — likely defines zone segmentation rules and approved data transfer mechanisms

Recommendation: engage your cybersecurity and legal/compliance teams in the first two weeks of Phase 0 to confirm obligations before architecture is finalized.

# 10. Immediate Next Steps

- Schedule Phase 0 kickoff with OT Operations, IT, SCADA Engineering, and Cybersecurity

- Begin asset and log source inventory (target: complete within 3 weeks)

- Initiate compliance obligation review with legal/regulatory team

- Review ServiceNow CMDB for completeness of in-scope equipment CIs

- Shortlist 2–3 log aggregation platform candidates for evaluation in Phase 1

- Identify pilot substation for Phase 1 PoC deployment